{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["Dataset","Goal Seek","With Macro Button","Prompt"],"not_rendered":{"charts":0,"images":2,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Dataset","index":0,"n_rows":13,"n_cols":6,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,5]]}
[]
[null,"Project Time Line"]
[]
[null,"Weeks","Project Phase","Scheduled Hours","Worked Hours","Project Progress"]
[null,"Week-1","Idea Buliding",35,35,{"$f":"E5/D5","v":1}]
[null,"Week-2","Ground Survey",30,25,{"$f":"E6/D6","v":0.83333333333333337}]
[null,"Week-3","Planning",40,27,0.67500000000000004]
[null,"Week-4","Implementation",55,25,0.45454545454545453]
[null,"Week-5","Course Correction",20,5,0.25]
[null,"Week-6","Final Ground Work",80,15,0.1875]
[null,"Week-7","Verification",25,2,0.08]
[null,"Week-8","Completion",20,0,0]
[null,"Week-9","Review",15,0,0]

{"sheet":"Goal Seek","index":1,"n_rows":13,"n_cols":6,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,5]]}
[]
[null,"Project Time Line"]
[]
[null,"Weeks","Project Phase","Scheduled Hours","Worked Hours","Project Progress"]
[null,"Week-1","Idea Buliding",35,17.500000000000004,{"$f":"E5/D5","v":0.50000000000000011}]
[null,"Week-2","Ground Survey",30,15.000000000000002,{"$f":"E6/D6","v":0.50000000000000011}]
[null,"Week-3","Planning",40,20.000000000000004,0.50000000000000011]
[null,"Week-4","Implementation",55,27.499999999999986,0.49999999999999972]
[null,"Week-5","Course Correction",20,10,0.5]
[null,"Week-6","Final Ground Work",80,40,0.5]
[null,"Week-7","Verification",25,12.499999999999998,0.49999999999999994]
[null,"Week-8","Completion",20,10.000000000000002,0.50000000000000011]
[null,"Week-9","Review",15,7.5,0.5]

{"sheet":"With Macro Button","index":2,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,5]]}
[]
[null,"Project Time Line"]
[]
[null,"Weeks","Project Phase","Scheduled Hours","Worked Hours","Project Progress",null,"Desired Project progress"]
[null,"Week-1","Idea Buliding",35,null,{"$f":"E5/D5","v":0},null,0.5]
[null,"Week-2","Ground Survey",30,null,{"$f":"E6/D6","v":0}]
[null,"Week-3","Planning",40,null,0]
[null,"Week-4","Implementation",55,null,0]
[null,"Week-5","Course Correction",20,null,0]
[null,"Week-6","Final Ground Work",80,null,0]
[null,"Week-7","Verification",25,null,0]
[null,"Week-8","Completion",20,null,0]
[null,"Week-9","Review",15,null,0]

{"sheet":"Prompt","index":3,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,1,1,5]]}
[]
[null,"Project Time Line"]
[]
[null,"Weeks","Project Phase","Scheduled Hours","Worked Hours","Project Progress",null,"Desired Project progress"]
[null,"Week-1","Idea Buliding",35,17.500000000000004,{"$f":"E5/D5","v":0.50000000000000011},null,0.5]
[null,"Week-2","Ground Survey",30,15.000000000000002,{"$f":"E6/D6","v":0.50000000000000011},null,0.5]
[null,"Week-3","Planning",40,20.000000000000004,0.50000000000000011,null,0.5]
[null,"Week-4","Implementation",55,27.499999999999986,0.49999999999999972,null,0.5]
[null,"Week-5","Course Correction",20,10,0.5,null,0.5]
[null,"Week-6","Final Ground Work",80,40,0.5,null,0.5]
[null,"Week-7","Verification",25,12.499999999999998,0.49999999999999994,null,0.5]
[null,"Week-8","Completion",20,10.000000000000002,0.50000000000000011,null,0.5]
[null,"Week-9","Review",15,7.5,0.5,null,0.5]