## Input Data
Track Multiple Projects in Excel
Project | Task | Responsible Person | Start Date | Due Date | Days Require | Progress | Status
Project 1 | Task 1 | Person X | 2020-02-10 | 2020-02-17 | 7 | 100% | Completed
Project 1 | Task 2 | Person Y | 2020-02-16 | 2020-02-23 | 7 | 100% | Completed
Project 1 | Task 3 | Person Z | 2020-02-15 | 2020-02-23 | 8 | 100% | Completed
Project 1 | Task 4 | Person M | 2020-02-03 | 2020-02-10 | 7 | 100% | Completed
Project 1 | Task 5 | Person N | 2020-02-12 | 2020-02-21 | 9 | 100% | Completed
Project 1 | Task 6 | Person S | 2020-02-15 | 2020-02-22 | 7 | 100% | Completed
Project 1 | Task 7 | Person X | 2020-02-10 | 2020-02-25 | 15 | 100% | Completed
Project 1 | Task 8 | Person Y | 2020-02-17 | 2020-02-24 | 7 | 100% | Completed
Project 1 | Task 9 | Person Z | 2020-02-11 | 2020-02-20 | 9 | 100% | Completed
Project 1 | Task 10 | Person M | 2020-02-12 | 2020-03-07 | 24 | 100% | Completed
Project 2 | Task 11 | Person N | 2020-02-19 | 2020-02-26 | 7 | 98% | In Progress
Project 2 | Task 12 | Person S | 2020-02-13 | 2020-02-17 | 4 | 62% | In Progress
Project 2 | Task 13 | Person X | 2020-02-20 | 2020-02-24 | 4 | 58% | In Progress
Project 2 | Task 14 | Person Y | 2020-02-27 | 2020-03-05 | 7 | 45% | In Progress
Project 2 | Task 15 | Person Z | 2020-03-05 | 2020-03-12 | 7 | 12% | In Progress
Project 2 | Task 16 | Person M | 2020-03-12 | 2020-03-13 | 1 | 21% | In Progress
Project 2 | Task 17 | Person N | 2020-02-26 | 2020-03-04 | 7 | 31% | In Progress
Project 2 | Task 18 | Person S | 2020-03-14 | 2020-03-21 | 7 | 45% | In Progress
Project 3 | Task 19 | Person M | 2020-03-29 | 2020-04-25 | 27 | 2% | In Progress
Project 3 | Task 20 | Person X | 2020-04-14 | 2020-05-11 | 27 | 45% | In Progress
Project 3 | Task 21 | Person Y | 2020-04-28 | 2020-05-15 | 17 | 87% | In Progress
Project 3 | Task 22 | Person Z | 2020-06-23 | 2020-07-08 | 15 | 98% | In Progress
Project 3 | Task 23 | Person M | 2020-08-18 | 2020-09-05 | 18 | 13% | In Progress
Project 3 | Task 24 | Person N | 2020-09-13 | 2020-10-10 | 27 | 97% | In Progress
Project 3 | Task 25 | Person S | 2020-11-08 | 2020-11-26 | 18 | 100% | Completed
Project 3 | Task 26 | Person X | 2020-11-24 | 2020-12-14 | 20 | 45% | In Progress
Project 3 | Task 27 | Person Y | 2021-01-19 | 2021-01-28 | 9 | 1% | In Progress
Project 3 | Task 28 | Person Z | 2021-01-31 | 2021-02-12 | 12 | 21% | In Progress
Project 3 | Task 29 | Person M | 2021-02-05 | 2021-03-12 | 35 | 46% | In Progress
Project 4 | Task 30 | Person N | 2021-04-02 | 2021-04-27 | 25 | 45% | In Progress
Formulas:
Due Date = [Start Date]+7
Start Date = [Start Date, row above]+7
Start Date = [Start Date, row above]-6

## Project Performance
Project by Project Breakdown
|  |  |  | Total Day Spent Till Date | 251.6
Projects | Days Requires | %Progress | Remaining | Total Day Required | 394
Project 1 | 100 | 100% | 0% | Overall Project Completion | 63.86%
Project 2 | 44 | 46.5% | 53.5%
Project 3 | 225 | 50.45% | 49.55%
251.6

## Project Overview
Starting Date of the Project | 2020-02-03
End Date of the Project | 2021-04-27
Project Managers | Project Report
Manager X
Manager Y | Total Day Spent | 251.6
Manager Z | Total Day Remains | 142.4
Manager M | Overall Progress | 63.86%
Manager N | Progress Left | 36.14%
Manager S
Specific Manager Performance | Manager X
Total Day Requires | 73
Total Day Spent | 45.47
Total Day Remains | 27.53
Overall Progress | 62.29%
Progress Left | 37.71%
64%

## Gantt Chart
Task Serial | Responsible Person | Start Date | Due Date | Days Require | Progress | In Progress | Days spent | time axis 2020-02-03 to 2021-05-25
Task 1 | Manager X | 2020-02-10 | 2020-02-17 | 7 | 100% | Completed | 7 | bar: 2020-02-10 to 2020-02-17
Task 2 | Manager Y | 2020-02-16 | 2020-02-23 | 7 | 100% | Completed | 7 | bar: 2020-02-16 to 2020-02-23
Task 3 | Manager Z | 2020-02-15 | 2020-02-23 | 8 | 100% | Completed | 8 | bar: 2020-02-15 to 2020-02-16
Task 4 | Manager M | 2020-02-03 | 2020-02-10 | 7 | 100% | Completed | 7 | bar: 2020-02-03 to 2020-02-10
Task 5 | Manager N | 2020-02-12 | 2020-02-21 | 9 | 100% | Completed | 9 | bar: 2020-02-12 to 2020-02-18
Task 6 | Manager S | 2020-02-15 | 2020-02-22 | 7 | 100% | Completed | 7 | bar: 2020-02-15 to 2020-02-19
Task 7 | Manager X | 2020-02-10 | 2020-02-25 | 15 | 100% | Completed | 15 | bar: 2020-02-10 to 2020-02-19
Task 8 | Manager Y | 2020-02-17 | 2020-02-24 | 7 | 100% | Completed | 7
Task 9 | Manager Z | 2020-02-11 | 2020-02-20 | 9 | 100% | Completed | 9
Task 10 | Manager M | 2020-02-12 | 2020-03-07 | 24 | 100% | Completed | 24
Task 11 | Manager N | 2020-02-19 | 2020-02-26 | 7 | 98% | In Progress | 6.86
Task 12 | Manager S | 2020-02-13 | 2020-02-17 | 4 | 62% | In Progress | 2.48
Task 13 | Manager X | 2020-02-20 | 2020-02-24 | 4 | 58% | In Progress | 2.32
Task 14 | Manager Y | 2020-02-27 | 2020-03-05 | 7 | 45% | In Progress | 3.15
Task 15 | Manager Z | 2020-03-05 | 2020-03-12 | 7 | 12% | In Progress | 0.84 | bar: 2020-03-05 to 2020-03-12
Task 16 | Manager M | 2020-03-12 | 2020-03-13 | 1 | 21% | In Progress | 0.21 | bar: 2020-03-12 to 2020-03-13
Task 17 | Manager N | 2020-02-26 | 2020-03-04 | 7 | 31% | In Progress | 2.17 | bar: 2020-02-26 to 2020-03-04
Task 18 | Manager S | 2020-03-14 | 2020-03-21 | 7 | 45% | In Progress | 3.15 | bar: 2020-03-14 to 2020-03-21
Task 19 | Manager N | 2020-03-29 | 2020-04-25 | 27 | 2% | In Progress | 0.54 | bar: 2020-03-29 to 2020-04-19
Task 20 | Manager X | 2020-04-14 | 2020-05-11 | 27 | 45% | In Progress | 12.15 | bar: 2020-04-14 to 2020-05-11
Task 21 | Manager Y | 2020-04-28 | 2020-05-15 | 17 | 87% | In Progress | 14.79 | bar: 2020-04-28 to 2020-05-15
Task 22 | Manager Z | 2020-06-23 | 2020-07-08 | 15 | 98% | In Progress | 14.7 | bar: 2020-06-23 to 2020-07-08
Task 23 | Manager M | 2020-08-18 | 2020-09-05 | 18 | 13% | In Progress | 2.34 | bar: 2020-08-18 to 2020-09-05
Task 24 | Manager N | 2020-09-13 | 2020-10-10 | 27 | 97% | In Progress | 26.19 | bar: 2020-09-13 to 2020-10-10
Task 25 | Manager S | 2020-11-08 | 2020-11-26 | 18 | 100% | Completed | 18 | bar: 2020-11-08 to 2020-11-26
Task 26 | Manager X | 2020-11-24 | 2020-12-14 | 20 | 45% | In Progress | 9 | bar: 2020-11-24 to 2020-12-14
Task 27 | Manager Y | 2021-01-19 | 2021-01-28 | 9 | 1% | In Progress | 0.09 | bar: 2021-01-19 to 2021-01-28
Task 28 | Manager Z | 2021-01-31 | 2021-02-12 | 12 | 21% | In Progress | 2.52 | bar: 2021-01-31 to 2021-02-12
Task 29 | Manager M | 2021-02-05 | 2021-03-12 | 35 | 46% | In Progress | 16.1 | bar: 2021-02-05 to 2021-03-12
Task 30 | Manager N | 2021-04-02 | 2021-04-27 | 25 | 56% | In Progress | 14
3