## Activity Schedule
Activity Schedule
Label | Description | Predecessor | Duration (Days)
A | Approval of Proposal | None | 7
B | Construction Plan Development | A | 10
C | Local Case Study | A | 15
D | Utility Service Avalibility | A | 4
E | Write Detail Study Report | B, C | 8
F | Final Approval from Authority | B, C, D | 12
G | Completion of Construction | F | 190
H | Open for Customers | E, G | 45

## Network Diagram
Creating Network Diagram

## Flow Chart
Creating Network Flow Chart