## CPM Network Diagram
Creation of CPM Network Diagram |  |  | Creation of CPM Network Diagram
Project Activity | Time (days) | Predecessor (s) | [6 empty] | 3 | 4 | 7
A | 3 | None |  |  |  | 0 | 3 | 3 | C
B | 2 | None |  |  |  | A
C | 4 | A | [6 empty] | 3 | 3 | 6
D | 3 | A | [6 empty] | D |  |  | 7 | 1 | 8
E | 5 | B | 0 | 0 | 0 | [6 empty] | G |  |  | 10 | 2 | 12
F | 4 | B | Start | [5 empty] | 2 | 5 | 7 |  |  |  | I
G | 1 | D, E | [6 empty] | E |  |  | 6 | 4 | 10
H | 4 | F |  |  |  | 0 | 2 | 2 |  |  |  | H
I | 2 | C, G, H |  |  |  | B |  |  | 2 | 4 | 6
F