## Workplan
Creating Workflow Management Template
Project | Task | Responsible Person | Starting Date | Due Date
Project-1 | Task 1 | Manager X | 2022-01-01 | 2022-01-20
Project-1 | Task 2 | Manager Y | 2022-01-02 | 2022-01-21
Project-1 | Task 3 | Manager Z | 2022-01-04 | 2022-01-22
Project-1 | Task 4 | Manager P | 2022-01-04 | 2022-01-23
Project-1 | Task 5 | Manager Q | 2022-01-05 | 2022-01-24
Project-1 | Task 6 | Manager R | 2022-01-05 | 2022-01-25
Project-1 | Task 7 | Manager S | 2022-01-06 | 2022-01-26
Project-1 | Task 8 | Manager T | 2022-01-06 | 2022-01-27
Project-1 | Task 9 | Manager U | 2022-01-06 | 2022-01-28
Project-1 | Task 10 | Manager U | 2022-01-06 | 2022-01-29
Project-1 | Task 11 | Manager V | 2022-01-11 | 2022-01-30
Project-1 | Task 12 | Manager F | 2022-01-12 | 2022-01-31

## Workflow Management
Creating Workflow Management Template
Project | Task | Responsible Person | Starting Date | Due Date | Days Spent | Days Required | Progress | Status
Project-1 | Task 1 | Manager X | 2022-01-01 | 2022-01-20 | 9 | 19 | 47.37% | In Progress
Project-1 | Task 2 | Manager Y | 2022-01-02 | 2022-01-21 | 10 | 19 | 52.63% | In Progress
Project-1 | Task 3 | Manager Z | 2022-01-04 | 2022-01-22 | 6 | 18 | 33.33% | In Progress
Project-1 | Task 4 | Manager P | 2022-01-04 | 2022-01-23 | 9 | 19 | 47.37% | In Progress
Project-1 | Task 5 | Manager Q | 2022-01-05 | 2022-01-24 | 19 | 19 | 100% | Completed
Project-1 | Task 6 | Manager R | 2022-01-05 | 2022-01-25 | 20 | 20 | 100% | Completed
Project-1 | Task 7 | Manager S | 2022-01-06 | 2022-01-26 | 10 | 20 | 50% | In Progress
Project-1 | Task 8 | Manager T | 2022-01-06 | 2022-01-27 | 11 | 21 | 52.38% | In Progress
Project-1 | Task 9 | Manager U | 2022-01-06 | 2022-01-28 | 12 | 22 | 54.55% | In Progress
Project-1 | Task 10 | Manager U | 2022-01-06 | 2022-01-29 | 23 | 23 | 100% | Completed
Project-1 | Task 11 | Manager V | 2022-01-11 | 2022-01-30 | 10 | 19 | 52.63% | In Progress
Project-1 | Task 12 | Manager F | 2022-01-12 | 2022-01-31 | 5 | 19 | 26.32% | In Progress

## Workflow Management chart
Creating Workflow Management Template
Task | Days Spent | Days Required | Progress | Remaining | Status
Task 1 | 9 | 19 | 47.37% | 52.63% | In Progress
Task 2 | 10 | 19 | 52.63% | 47.37% | In Progress
Task 3 | 6 | 18 | 33.33% | 66.67% | In Progress
Task 4 | 9 | 19 | 47.37% | 52.63% | In Progress
Task 5 | 19 | 19 | 100% | 0% | Completed
Task 6 | 20 | 20 | 100% | 0% | Completed
Task 7 | 10 | 20 | 50% | 50% | In Progress
Task 8 | 11 | 21 | 52.38% | 47.62% | In Progress
Task 9 | 12 | 22 | 54.55% | 45.45% | In Progress
Task 10 | 23 | 23 | 100% | 0% | Completed
Task 11 | 10 | 19 | 52.63% | 47.37% | In Progress
Task 12 | 5 | 19 | 26.32% | 73.68% | In Progress
| Overall Project Completion |  |  | 59.71% |  | Project Workflow Report |  |  | Task Status
[6 empty] | Total day Required |  | 238 | Completed | 3 | 25%
[6 empty] | Total day spent |  | 144 | In Progress | 9 | 75%
[6 empty] | Overall Progress |  | 60.5%
Task Status
[7 empty] | Days Spent | Days Required | Completed | In Progress
[7 empty] | 144 | 238 | 3 | 9

## Final Output
Task | Days Spent | Days Required | Progress | Remaining | Status
Task 1 | 9 | 19 | 47.37% | 52.63% | In Progress
Task 2 | 10 | 19 | 52.63% | 47.37% | In Progress
Task 3 | 6 | 18 | 33.33% | 66.67% | In Progress
Task 4 | 9 | 19 | 47.37% | 52.63% | In Progress
Task 5 | 19 | 19 | 100% | 0% | Completed
Task 6 | 20 | 20 | 100% | 0% | Completed
Task 7 | 10 | 20 | 50% | 50% | In Progress
Task 8 | 11 | 21 | 52.38% | 47.62% | In Progress
Task 9 | 12 | 22 | 54.55% | 45.45% | In Progress
Task 10 | 23 | 23 | 100% | 0% | Completed
Task 11 | 10 | 19 | 52.63% | 47.37% | In Progress
Task 12 | 5 | 19 | 26.32% | 73.68% | In Progress