## Summary
Example of Project Cost Estimation
Details of the Project
Project Name | Total Income during the period |  | XYZ |  | Client Name |  | ABC Enterprise
Project Number | Total Expenses during the period |  | KXX102 |  | Start Date |  | 2023-01-01
Project Manager | Total Savings during the period |  | Mr. X |  | Probable End Date |  | 2023-03-26
S.L. | Particulars | Material Cost |  | Labor Cost |  | Fixed Cost | Miscellaneous Cost | Estimated Cost
|  | Units | Per Unit | Hours | Per Hour
Phase A
1 | Job 1 | 650 | 19 | 8 | 45 | 2500 | 4200 | 19410
2 | Job 2 | 300 | 22 | 8 | 60 | 4500 | 3500 | 15080
3 | Job 3 | 380 | 15 | 8 | 55 | 4000 | 3000 | 13140
(A) | Total | 24650 |  | 1280 |  | 11000 | 10700 | 47630
Phase B
1 | Job 4 | 415 | 19 | 8 | 45 | 4500 | 3800 | 16545
2 | Job 5 | 358 | 25 | 7.5 | 60 | 3200 | 4500 | 17100
(B) | Total | 16835 |  | 810 |  | 7700 | 8300 | 33645
Phase C
1 | Job 6 | 225 | 35 | 9 | 55 | 3500 | 4000 | 15870
2 | Job 7 | 458 | 18 | 8 | 60 | 4800 | 3500 | 17024
(C) | Total | 16119 |  | 975 |  | 8300 | 7500 | 32894
Total of Project ( A + B + C ) |  | 57604 |  | 3065 |  | 27000 | 26500 | 114169
©ExcelDemy 2022

## Template
Example of Project Cost Estimation
Details of the Project
Project Name | Total Income during the period |  |  |  | Client Name
Project Number | Total Expenses during the period |  |  |  | Start Date
Project Manager | Total Savings during the period |  |  |  | Probable End Date
S.L. | Particulars | Material Cost |  | Labor Cost |  | Fixed Cost | Miscellaneous Cost | Estimated Cost
|  | Units | Per Unit | Hours | Per Hour
Phase A
1 | Job 1 | [6 empty] | 0
2 | Job 2 | [6 empty] | 0
3 | Job 3 | [6 empty] | 0
(A) | Total | 0 |  | 0 |  | 0 | 0 | 0
Phase B
1 | Job 4 | [6 empty] | 0
2 | Job 5 | [6 empty] | 0
(B) | Total | 0 |  | 0 |  | 0 | 0 | 0
Phase C
1 | Job 6 | [6 empty] | 0
2 | Job 7 | [6 empty] | 0
(C) | Total | 0 |  | 0 |  | 0 | 0 | 0
Total of Project ( A + B + C ) |  | 0 |  | 0 |  | 0 | 0 | 0
©ExcelDemy 2022