## Template
Project Time Estimation for "X" Company
SL No. | Tasks | Designation | Name | Planned Weeks | Estimated Weeks | Cost per hour | Planned Cost | Estimated Cost | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
1 | Task 3 | Manager | Ursula | 2 | 1.55 | 67 | 5360 | 4154 | 15% | 20% | 10% | 30% | 60% | 10% |  |  |  | 10%
2 | Task 1 | Team Leader | Jenny | 4 | 1.2 | 14 | 2240 | 672 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
3 | Task 4 | Team Leader | Jenny | 3 | 1.65 | 41 | 4920 | 2706 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
4 | Task 6 | Manager | Ursula | 5 | 2 | 15 | 3000 | 1200 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
5 | Task 7 | Designer | Lily | 2 | 1.2 | 60 | 4800 | 2880 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
6 | Task 1 | Developer | Inaya | 5 | 1.65 | 14 | 2800 | 924 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
7 | Task 4 | Supervisor | Katherine | 4 | 2 | 41 | 6560 | 3280 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
8 | Task 6 | Supervisor | Katherine | 2 | 1.2 | 15 | 1200 | 720 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
9 | Task 4 | Manager | Ursula | 5 | 1.65 | 41 | 8200 | 2706 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
10 | Task 3 | Developer | Inaya | 3 | 2 | 67 | 8040 | 5360 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
11 | Task 4 | Project Manager | Jackson | 2 | 1.2 | 41 | 3280 | 1968 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
12 | Task 5 | Manager | Ursula | 4 | 1.65 | 21 | 3360 | 1386 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
13 | Task 3 | Project Manager | Jackson | 5 | 2 | 67 | 13400 | 5360 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
14 | Task 5 | Team Leader | Jenny | 4 | 1.2 | 21 | 3360 | 1008 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
15 | Task 7 | Developer | Inaya | 2 | 1.65 | 60 | 4800 | 3960 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
16 | Task 4 | Designer | Lily | 1 | 2 | 41 | 1640 | 3280 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
17 | Task 4 | Supervisor | Katherine | 3 | 1.2 | 41 | 4920 | 1968 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
18 | Task 4 | Designer | Lily | 5 | 1.65 | 41 | 8200 | 2706 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
19 | Task 5 | Developer | Inaya | 1 | 1.9 | 21 | 840 | 1596 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10%
|  |  |  | Total Weeks | 30.55 |  | Total Cost | 47834

## Data
List of Tasks, Employees, Costs
Tasks | Designation | Name | Cost per hour
Task 1 | Project Manager | Jackson | 14
Task 2 | Team Leader | Jenny | 39
Task 3 | Manager | Ursula | 67
Task 4 | Developer | Inaya | 41
Task 5 | Designer | Lily | 21
Task 6 | Supervisor | Katherine | 15
Task 7 | Developer | Michael | 60
Task 8 | Designer | Henry | 4
Task 9 | Project Manager | Jefferson | 39
Task 10 | Team Leader | Denver | 79
Task 11 | Manager | Emily | 79
Task 12 | Team Leader | Sheldon | 85

## Template (2)
Project Time Estimation for "X" Company
SL No. | Tasks | Designation | Name | Planned Weeks | Estimated Weeks | Cost per hour | Planned Cost | Estimated Cost | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
1 | Task 3 | Manager | Ursula | 2 | 1.55 | 67 | 5360 | 4154 | 15% | 20% | 10% | 30% | 60% | 10% |  |  |  | 10%
2 | Task 1 | Team Leader | Jenny | 4 | 1.2 | 14 | 2240 | 672 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
3 | Task 4 | Team Leader | Jenny | 3 | 1.65 | 41 | 4920 | 2706 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
4 | Task 6 | Manager | Ursula | 5 | 2 | 15 | 3000 | 1200 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
5 | Task 7 | Designer | Lily | 2 | 1.2 | 60 | 4800 | 2880 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
6 | Task 1 | Developer | Inaya | 5 | 1.65 | 14 | 2800 | 924 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
7 | Task 4 | Supervisor | Katherine | 4 | 2 | 41 | 6560 | 3280 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
8 | Task 6 | Supervisor | Katherine | 2 | 1.2 | 15 | 1200 | 720 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
9 | Task 4 | Manager | Ursula | 5 | 1.65 | 41 | 8200 | 2706 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
10 | Task 3 | Developer | Inaya | 3 | 2 | 67 | 8040 | 5360 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
11 | Task 4 | Project Manager | Jackson | 2 | 1.2 | 41 | 3280 | 1968 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
12 | Task 5 | Manager | Ursula | 4 | 1.65 | 21 | 3360 | 1386 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
13 | Task 3 | Project Manager | Jackson | 5 | 2 | 67 | 13400 | 5360 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
14 | Task 5 | Team Leader | Jenny | 4 | 1.2 | 21 | 3360 | 1008 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
15 | Task 7 | Developer | Inaya | 2 | 1.65 | 60 | 4800 | 3960 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
16 | Task 4 | Designer | Lily | 1 | 2 | 41 | 1640 | 3280 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10% |  | 10%
17 | Task 4 | Supervisor | Katherine | 3 | 1.2 | 41 | 4920 | 1968 | 50% | 10% | 10% | 20% | 10% | 10% | 10%
18 | Task 4 | Designer | Lily | 5 | 1.65 | 41 | 8200 | 2706 | 10% | 15% | 30% | 15% | 40% | 30% | 25%
19 | Task 5 | Developer | Inaya | 1 | 1.9 | 21 | 840 | 1596 | 50% | 40% | 10% | 30% | 20% | 10% | 20% | 10%
|  |  |  | Total Weeks | 30.55 |  | Total Cost