## Data Set
Risk Burndown Chart in Excel | [8 empty] | Practice
Original Data | [8 empty] | Original Data
Feature | Estimate | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | Remaining | Feature | Estimate | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | Remaining
Brainstorming | 600 | 120 | 120 | 80 | 80 | 70 | 60 | 70 | Brainstorming | [7 empty] | 0
Business Analysis | 600 | 150 | 110 | 90 | 60 | 60 | 80 | 50 | Business Analysis | [7 empty] | 0
Design | 600 | 120 | 120 | 110 | 60 | 80 | 85 | 25 | Design | [7 empty] | 0
Programming | 600 | 120 | 120 | 110 | 70 | 80 | 90 | 10 | Programming | [7 empty] | 0
Integration | 600 | 110 | 95 | 100 | 65 | 100 | 105 | 25 | Integration | [7 empty] | 0
Quality Assurance | 600 | 85 | 90 | 95 | 80 | 100 | 100 | 50 | Quality Assurance | [7 empty] | 0
Modified Data for Chart | [8 empty] | Modified Data for Chart
Feature | Start | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 |  | Feature | Start | M 1 | M 2 | M 3 | M 4 | M 5 | M 6
Planned Work |  | 600 | 600 | 600 | 600 | 600 | 600 |  | Planned Work |  | 0 | 0 | 0 | 0 | 0 | 0
Actual Work |  | 705 | 655 | 585 | 415 | 490 | 520 |  | Actual Work |  | 0 | 0 | 0 | 0 | 0 | 0
Remaining Work | 3600 | 2895 | 2240 | 1655 | 1240 | 750 | 230 |  | Remaining Work | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ideal Burndown | 3600 | 3000 | 2400 | 1800 | 1200 | 600 | 0 |  | Ideal Burndown | 0 | 0 | 0 | 0 | 0 | 0 | 0