## Dataset
Production Time Estimation for a Leather Shoe
Time Projection | Feature 1 | Feature 2 | Feature 3
Day 0 | 2 | 6 | 8
Day 1 | 1 |  | 2
Day 2 |  | 1 | 1
Day 3 |  | 2 | 1
Day 4 |  | 1
Day 5 |  |  | 1
Day 6 |  |  | 1
Day 7 | 1 | 1 | 1
Day 8 |  | 1 | 1

## Sprint Burndown Chart
Creating Sprint Burndown Chart
Time Projection | Feature 1 | Feature 2 | Feature 3 | Remaining Days | Ideal Trend
Day 0 | 2 | 6 | 8 | 16 | 16
Day 1 | 1 |  | 2 | 13 | 14
Day 2 |  | 1 | 1 | 11 | 12
Day 3 |  | 2 | 1 | 8 | 10
Day 4 |  | 1 |  | 7 | 8
Day 5 |  |  | 1 | 6 | 6
Day 6 |  |  | 1 | 5 | 4
Day 7 | 1 | 1 | 1 | 2 | 2
Day 8 |  | 1 | 1 | 0 | 0

## Do It Yourself
Do It Yourself
Time Projection | Feature 1 | Feature 2 | Feature 3
Day 0 | 2 | 6 | 8
Day 1 | 1 |  | 2
Day 2 |  | 1 | 1
Day 3 |  | 2 | 1
Day 4 |  | 1
Day 5 |  |  | 1
Day 6 |  |  | 1
Day 7 | 1 | 1 | 1
Day 8 |  | 1 | 1