## Dataset
Creating Workflow Tracker
Task | Starting Date | Due Date
Task 1 | 2022-01-01 | 2022-01-20
Task 2 | 2022-01-02 | 2022-01-21
Task 3 | 2022-01-04 | 2022-01-22
Task 4 | 2022-01-04 | 2022-01-23
Task 5 | 2022-01-05 | 2022-01-24
Task 6 | 2022-01-05 | 2022-01-25
Task 7 | 2022-01-06 | 2022-01-26
Task 8 | 2022-01-06 | 2022-01-27

## Progress Status
Creating Workflow Tracker
Task | Starting Date | Due Date | Days Spent | Days Required | Progress | Status
Task 1 | 2022-01-01 | 2022-01-20 | 9 | 19 | 47.37% | In Progress
Task 2 | 2022-01-02 | 2022-01-21 | 10 | 19 | 52.63% | In Progress
Task 3 | 2022-01-04 | 2022-01-22 | 6 | 18 | 33.33% | In Progress
Task 4 | 2022-01-04 | 2022-01-23 | 9 | 19 | 47.37% | In Progress
Task 5 | 2022-01-05 | 2022-01-24 | 19 | 19 | 100% | Complete
Task 6 | 2022-01-05 | 2022-01-25 | 20 | 20 | 100% | Complete
Task 7 | 2022-01-06 | 2022-01-26 | 10 | 20 | 50% | In Progress
Task 8 | 2022-01-06 | 2022-01-27 | 11 | 21 | 52.38% | In Progress

## Workflow Progress chart
Creating Workflow Progress Tracker
Task | Days Spent | Days Required | Progress | Remaining | Status
Task 1 | 9 | 19 | 47.37% | 52.63% | In Progress
Task 2 | 10 | 19 | 52.63% | 47.37% | In Progress
Task 3 | 6 | 18 | 33.33% | 66.67% | In Progress
Task 4 | 9 | 19 | 47.37% | 52.63% | In Progress
Task 5 | 19 | 19 | 100% | 0% | Complete
Task 6 | 20 | 20 | 100% | 0% | Complete
Task 7 | 10 | 20 | 50% | 50% | In Progress
Task 8 | 11 | 21 | 52.38% | 47.62% | In Progress
| Overall Project Completion |  |  | 60.39%
Project Workflow Report |  |  | Task Status
Total day Required | 155 |  | Completed | 2 | 25%
Total day spent | 94 |  | In Progress | 6 | 75%
Overall Progress | 60.65%
Task Status