## Dataset
Gantt Chart in Excel
Task | Start Date | End Date | Duration
Project Planning | 2023-07-01 | 2023-07-07 | 6
Market Research | 2023-07-08 | 2023-07-21 | 13
Product Development | 2023-07-22 | 2023-08-18 | 27
Marketing Strategy | 2023-08-19 | 2023-08-31 | 12
Launch Preparation | 2023-09-01 | 2023-09-15 | 14
Product Launch | 2023-09-16 | 2023-09-17 | 1
Post-launch Evaluation | 2023-09-18 | 2023-09-30 | 12
We will create Gantt Chart using this dataset.

## Chart
The Gantt Chart
Task | Start Date | End Date | Duration
Project Planning | 2023-07-01 | 2023-07-07 | 6
Market Research | 2023-07-08 | 2023-07-21 | 13
Product Development | 2023-07-22 | 2023-08-18 | 27
Marketing Strategy | 2023-08-19 | 2023-08-31 | 12
Launch Preparation | 2023-09-01 | 2023-09-15 | 14
Product Launch | 2023-09-16 | 2023-09-17 | 1
Post-launch Evaluation | 2023-09-18 | 2023-09-30 | 12