## main
Network Diagram in Excel
ES | Label | EF | ES | E | EF
Description |  |  | Detail Study Report
LS | Days | LF | LS | 8 | LF
0 | A | 7 | ES | F | EF
Approval of Proposal |  |  | Final Approval
LS | 7 | LF | LS | 12 | LF
7 | B | 17 | ES | G | EF
Construction Plan Development |  |  | Complete Construction
LS | 10 | LF | LS | 190 | LF
ES | C | EF | ES | H | EF
Local Case Study |  |  | Open for Customers
LS | 15 | LF | LS | 45 | LF
ES | D | EF
Utility Service Availability
LS | 4 | LF

## basic
Creating Network Diagram in Excel
ES | Label | EF | ES | E | EF
Description |  |  | Detail Study Report
LS | Days | LF | LS | 8 | LF
0 | A | 7 | ES | F | EF
Approval of Proposal |  |  | Final Approval
LS | 7 | LF | LS | 12 | LF
7 | B | 17 | ES | G | EF
Construction Plan Development |  |  | Complete Construction
LS | 10 | LF | LS | 190 | LF
ES | C | EF | ES | H | EF
Local Case Study |  |  | Open for Customers
LS | 15 | LF | LS | 45 | LF
ES | D | EF
Utility Service Availability
LS | 4 | LF

## project
Drawing Project Network Diagram in Excel