## Sheet1
Creating Burndown Chart
Department | Estimated Hours | Week1 | Week2 | Week3 | Week4 | Week5 | Hours Left
Designing | 80 | 20 | 15 | 12 | 10 | 8 | 15
Manufacturing | 100 | 10 | 15 | 20 | 22 | 18 | 15
Testing | 60 | 10 | 10 | 10 | 10 | 10 | 10
Optimizing | 80 | 5 | 8 | 15 | 12 | 20 | 20
Setting | Start | Week1 | Week2 | Week3 | Week4 | Week5
Planned Hours |  | 64 | 64 | 64 | 64 | 64
Actual Hours |  | 45 | 48 | 57 | 54 | 56
Remaining Hours | 320 | 275 | 227 | 170 | 116 | 60
Total Breakdown | 320 | 256 | 192 | 128 | 64 | 0

## Sheet2
Creating Burndown Chart
Department | Estimated Hours | Week1 | Week2 | Week3 | Week4 | Week5 | Hours Left
Designing | 80 | 20 | 15 | 12 | 10 | 8 | 15
Manufacturing | 100 | 10 | 15 | 20 | 22 | 18 | 15
Testing | 60 | 10 | 10 | 10 | 10 | 10 | 10
Optimizing | 80 | 5 | 8 | 15 | 12 | 20 | 20
Setting | Start | Week1 | Week2 | Week3 | Week4 | Week5
Planned Hours |  | 64 | 64 | 64 | 64 | 64
Actual Hours |  | 45 | 48 | 57 | 54 | 56
Remaining Hours | 320 | 275 | 227 | 170 | 116 | 60
Total Breakdown | 320 | 256 | 192 | 128 | 64 | 0